## Slide 1
CaBuCo
Project information session, 27th November, 2024
Online event
Peter Kiska – Coordinator

## Slide 2: Project details
Lead institute: Czech Metrology Institute
Coordinator: Peter Kiska
Start date: 1st June, 2024
Duration: 48 months
Budget: 1 mil. EUR
Full name: Capacity Building Coordination
Akronym: CaBuCo
Project number: 23CBC01

## Slide 3: Overview
The overall objective of this coordination project is to assist EURAMET’s bodies to achieve impact for the European metrology community by coordinating and managing the capacity building instruments used for and aligned with EURAMET’s Capacity Building Strategy:
    Researcher Mobility Support (RMS)
    Mentoring Scheme Award (MSA)
    Training events (Trainings, Workshops and Summer Schools)
The CaBuCo project will be executed through three open calls a year.
Evaluation will take place every four months (9 times in total during lifetime period of the project).
RMS, MSA, TE guides and templates were published on the project website link here.
Online application process.
https://cabuco.cmi.gov.cz/

## Slide 4: Evaluation process
Step 1 | CMI/Project | Perform eligibility criteria checks | Around 2 weeks
Step 2 | Stakeholder committee | Review and mark against the Excellence, Impact and Efficiency of the implementation criteria | Around 2 weeks
Step 3 | Stakeholder committee | Prioritise and decide which applications are selected for funding. | 
Evaluation process will be provided as 3 steps process.
Stakeholder Committee works as independent body.
Coordinator appoints three independent experts from the SC who will evaluate the assigned CB activity proposal.

## Slide 5: Project budget
Chart: Foreseen allocation of funds in %
| RMS | MSA | Training events | Capacity Building Coordination
 | 403375 | 84000 | 253300 | 259325
 | k EUR
RMS | 403
MSA | 84
Training events | 253
Capacity Building Coordination | 259

## Slide 6: Gantt chart
4 months
2023
24/25
Call 1 open
Result
Applicant
CMI
Stakeholder Committee
Final list
Notification letter
October
November
December
January
February
March
April
May
June
Today
53 days
Mar 1 - May 13
Application is submitted
May 15 - Nov 30
2 weeks
50 days
Jun 3 - Aug 13
50 days
Aug 12 - Oct 22
1st week of March
July
Annoncement to Applicants
Call 1 Open
October 1, 2024
Call 1 Closed
Call 2 Open
Final List
Notification letter
2 weeks
1st week of March
January 31, 2025
Call 1 is OPEN from 1st October, 2024.

## Slide 7: Research Mobility Support (RMS)
This instrument supports researchers from EURAMET NMIs and DIs to join an organisation in a different country to their employer (a EURAMET NMI or DI or other institution that can host suitable research) for between one to nine months, in order to perform research in the selected field.
Applicants: EURAMET NMIs and DIs and NMIs and DIs from EU member states and countries associated to Horizon Europe.
Host Organisation: EURAMET NMIs or DIs and other institutions (e.g., universities, public research organisations), that are or have been participating in Partnership JRPs and located in different country.
Duration: 1-9 months.
Financial allowances:
• Living allowance of €2400 (plus a country correction factor) per month to cover accommodation, subsistence, and local travel.
• Travel – a fixed allowance of €500 paid every 3 months.
• Development – maximum amount of €1000 can be used for conference attendanc, during the lifetime of the RMS.
Payment: the employing organisation.
Pre financing 80% of the budget, final payment 20% (60 days after approval of final report).

## Slide 8: Research Mobility Support (RMS)
Typical activities:
Must include research and/or development.
Comprise an additional package of research to an associated Partnership JRP. The work of the RMS must be both relevant and additional to the associated JRP’s objectives.
Add value to an associated JRP; and is suitably scientifically and/or technologically challenging.
Include scientific training and transfer of knowledge.
Implement a new or improved measurement/calibration service.
Implement new or improved measurement tools/artefacts.
Pilot comparisons of new technologies.

## Slide 9: Mentoring Scheme Award (MSA)
MSA provides a platform for staff from two different metrological institutes (EURAMET NMI or DI), in different countries, to set up a partnership and work together on a relevant topic, such as technical, managerial, comparisons or traceability.
Applicant: EURAMET NMIs and DIs and NMIs and DIs from EU member states and countries associated to Horizon Europe.
Host Organisation: EURAMET NMIs or DIs and other institutions
Duration: 2-6 weeks
Financial allowances: project will reimburse actual costs incurred for travel, accommodation and subsistence for MSA recipients for their visit(s) to the counterpart organisation according to the accounting rules of their Employing organisation (financial estimates need to be send within application)
Typical activities: support exchange of expertise on technical and managerial topics

## Slide 10: Training events (Trainings, Workshops and Summer Schools)
For EURAMET to maintain and further expand its capacity building efforts across Europe. Within this aktivity, project develop the technical skills of existing staff at NMIs/DIs, support the development of newly qualified staff for all EURAMET NMIs/DIs and prepare them for work in a metrological laboratory.
Applicants: EURAMET NMIs/Dis.
Participants: Staff members of EURAMET NMIs and DIs, students, representatives of RMOs
Duration:
- Training courses and workshops to be held as 1–5 days events.
- Summer Schools held as 3-10 days events.
Typical activities: Training events would cover several topics that are relevant to NMI and DIs. Typical topics would be prioritised and decided on annually by EURAMET bodies.
Financial allowance: project will reimburse the actual costs incurred for travel and subsistence of key speakers, venue hire (if required) and catering costs according to the accounting rules of the hosting organisation

## Slide 11: Highlights
First activities funded by the project will be implemented from mid March, 2025.
Call 1 will closed on 31st January, 2025
Q&A

## Slide 12
Thank you for your attention!